# Project of Shapes 
The project has been funded with support from the European Commission!

# Plan of the first year

### Transnational project meetings and learning activities

1.1 TPM (transnational project meeting): Czech Republic  
10th−14th December 2016
Agenda: 
– plan of the first project year: meetings, activities, products, tasks (in this document)

– rules of cooperation and communication (in this document)

– contacts (2 from each school, emails, mobiles, addresses, facebooks…)

– announcements, promotion, notice-boards, facebook group, websites

– visit of the host school and presentation of the educational system in the Czech Rep.

– meeting report („minutes“) with the tasks, plans, terms, rules… (this document)see above

1.2 TLA (transnational learning activity): Czech Republic  
26th March – 1st April or 23rd−29th April 2017? 
(decision will have been done by 21st December by the Greek school)
Activities and products:
– common multilingual dictionary of geometry (homework, HW)
– workshops of painting/drawing/creating of regular shapes
– contests in working out geometrical puzzles [1] (HW)
– visit of a gallery or museum
– taking pictures in the city
– taking pictures in the nature

### Local activities

– information to teachers, students, local community with promotion
– creating a website, notice-board and a common facebook group
– implementation of a language preparation (voluntarily)
– organization of creating a geometrical dictionary
– preparation of puzzles/problems/rebuses/curiosities/delusions connected with geometry  (+ dissemination = multiplier event)
– uploading the websites
– taking and making photographs
– visiting gallery/museum/etc
– preparation of presentation on geometry! (+ dissemination = multiplier event)
– preparation of a story „Back in history“! (+ dissemination = multiplier event)
– creating cards (catalogue)!
– evaluation and dissemination of the first year results

### Local products

– School project web site. Notice-board at school. (Facebook group Shapes.) (P1)
– Multilingual dictionary of geometry: 100 items. By the middle of March 2017. (P2)
– 10 puzzles/problems/rebuses/curiosities/delusions connected with geometry (in English and in the mother language). By the middle of March 2017. (P7)
– Report on visit of a gallery/museum/sight (in English and in the mother language). By April 2017. (P5)
– Presentation on regular shapes on curves and figures. By June 2017. HW for next year. (P3)
– Story from history of shapes (in English and in the mother language). By June 2017. HW for next year. (P4)
– Catalogue of at least 100 cards with photos and description (in doc and in pdf). By June 2017. HW for next year. (P6)